## 
Known Issues Tracker
Provider Type | Number of Impacted Providers | Category | Issue | Date Issue Found | Number of Days Outstanding | Estimated Fix Date | Status | Resolution | Interest/Penalties Owed | Date Resolved | Tech Ops Incident/Problem Number
All | TBD | Claims | CCH has identified an error in upfront EDI rejection logic related to NPI and Taxonomy combinations verifying against NC Tracks. The logic was not reviewing the previous active spans which caused incorrect rejections based on a provider status on the DOS. | 2026-09-09 | 0 | 2026-10-01 | Open | System configuration logic is being updated. Claims impacted will be identified and will be reprocessed once the system fix is completed. No further action needed from providers at this time. | TBD |  | NA
All | TBD | Claims | CCH has identified an issue where prior WellCare members now assigned to Partners eligibility have incorrectly retained the same Member ID in the CCH claims system. The incorrect Member ID is causing claims to deny incorrectly for 'Ex28: Member Not Eligible on DOS'. | 2026-06-30 | 72 | 2026-09-18 | Open | System configuration logic is being updated. A manual process is in place to prevent further denials. Claims impacted will be identified and will be reprocessed once the system fix is completed. No further action needed from providers at this time. | TBD |  | NA
All | 674 | Claims | CCH has identified a subset of claims that were not included in the initial reprocessing of the Carolina Complete Health October 1, 2025, Fee Schedule Rate Reversal updates due to the volume and complexity of the required adjustments. While the majority of impacted claims were successfully reprocessed as of March 21, 2026, the following provider types require additional reprocessing: Physicians, Labs, Outpatient Hospitals, PCS, and National Contracts. At this time, no action is required from providers. Please do not resubmit claims for the purpose of expediting reprocessing. Note: This summary and reprocessing effort are independent of the reprocessing on the legacy WellCare platform. | 2026-05-07 | 85 | 2026-07-31 | Closed | System configuration logic is complete. Claims impacted have been identified, and reprocessing is in progress. No further action needed from providers at this time. | Yes | 2026-07-31
DME | 83 | Claims; Configuration | Identified an issue with claims denying EX35 DENY: BENEFIT MAXIMUM HAS BEEN REACHED and EXBe BENEFIT LIMITS MAY NOT BE EXCEEDED WITHOUT PRIOR AUTHORIZATION when the provider obtained a medical necessity pre-authorization to allow for additional units. (This item was previously closed on 9/05/25) | 2025-12-11 | 172 | 2026-06-01 | Closed | System configuration logic is complete. Claims impacted have been identified, and reprocessing is in progress. No further action needed from providers at this time. | Yes | 2026-06-01